## Scope
Persona | Module | Feature | Sub Feature | #pages | Complexity | Component | Form Factor | Milestone | Design (hrs) | Web UI | Services | AI | Mobile UI | DevOps | PO | PM | Design Strategy | Architect | QA Manual | QA Auto | Validation |  | Design (ReUse) | Web UI (ReUse) | Services (ReUse) | Mobile UI (ReUse) | Automation (ReUse) | ReUse Notes
| Registration | Registration | Email Signup | 3 | XS | Frontend | Responsive | Phase 1 |  | 6 | 0 |  | 6 | [5 empty] | 1.2 | 6 | 19.2 |  |  | 15 |  | 15
| Registration | Registration | Google Signup | 3 | XS | Frontend | Responsive | Phase 2 |  | 6 | 0 |  | 6 | [5 empty] | 1.2 | 6 | 19.2 |  |  | 15 |  | 15
| Registration | Registration | Linkedin Signup | 3 | XS | Frontend | Responsive | Phase 2 |  | 6 | 0 |  | 6 | [5 empty] | 1.2 | 6 | 19.2 |  |  | 15 |  | 15
| Registration | Registration | Invite-Based Registration | 3 | XS | Frontend | Responsive | Phase 3 |  | 6 | 0 |  | 6 | [5 empty] | 1.2 | 6 | 19.2 |  |  | 15 |  | 15
| Identification | Identification | Email Login | 3 | XS | Frontend | Responsive | Phase 1 |  | 5 | 0 |  | 5 | [5 empty] | 1 | 6 | 17 |  |  | 15 |  | 15
| Identification | Identification | Linkedin Login | 3 | XS | Frontend | Responsive | Phase 2 |  | 5 | 0 |  | 5 | [5 empty] | 1 | 6 | 17 |  |  | 15 |  | 15
| Identification | Identification | Google Login | 3 | XS | Frontend | Responsive | Phase 2 |  | 5 | 0 |  | 5 | [5 empty] | 1 | 6 | 17 |  |  | 15 |  | 15
| Identification | Identification | Session Management | 3 | XS | Frontend | Responsive | Phase 2 |  | 5 | 0 |  | 5 | [5 empty] | 1 | 6 | 17 |  |  | 15 |  | 15
| First Time Experience | First Time Experience | Welcome Flow | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| First Time Experience | First Time Experience | Role & Profile Setup | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| First Time Experience | First Time Experience | Topic Preferences | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| First Time Experience | First Time Experience | First Action Nudges | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Discovery | Discovery | Unified Search Bar | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Discovery | Discovery | Search Filters | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Discovery | Discovery | AI Semantic Search | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 | 24 | 3.9 | [5 empty] | 0.78 | 6 | 38.58 |  |  | 15 |  | 15
| Discovery | Discovery | Search Suggestions | 3 | XS | Frontend | Responsive | Phase 3 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Discovery | Discovery | Recent Searches | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Discovery | Global Search | People to follow | 3 | XS | Frontend | Responsive | Phase 3 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Account Profile | Account Profile | Basic Profile, KPIs | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Account Profile | User Profile | Proffesional experience section | 3 | XS | Frontend | Responsive | Phase 3 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Account Profile | User Profile | List of own posts | 3 | XS | Frontend | Responsive | Phase 3 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Account Profile | Account Profile | Activity Overview | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Account Profile | Account Profile | Badges & Contributions | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Account Profile | Account Profile | Privacy Controls | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Notification Hub | Notification Hub | In-App Alerts | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Notification Hub | Notification Hub | Email Notifications | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Notification Hub | Notification Hub | Push Notifications | 3 | XS | Frontend | Responsive | Phase 3 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Notification Hub | Notification Hub | Notification Settings | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Personalized Home Feed | Personalized Home Feed | Content Feed | 3 | XS | Frontend | Responsive | Phase 1 |  | 9 | 0 |  | 9 | [5 empty] | 1.8 | 6 | 25.8 |  |  | 15 |  | 15
| Personalized Home Feed | Home Feed | Create new post | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
101 | Personalized Home Feed | Personalized Home Feed | Feed Personalization | 3 | XS | Frontend | Responsive | Phase 1 |  | 9 | 0 | 40 | 9 | [5 empty] | 1.8 | 6 | 65.8 |  |  | 15 |  | 15
| Personalized Home Feed | Personalized Home Feed | Interaction | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Personalized Home Feed | Home Feed | Comments screen, interaction | 3 | XS | Frontend | Responsive | Phase 1 |  | 8.9 | 0 |  | 8.9 | [5 empty] | 1.78 | 6 | 25.58 |  |  | 10 |  | 10
| Personalized Home Feed | Home Feed | Share post interaction | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Message Section | Message Section | List of People, search function | 3 | XS | Frontend | Responsive | Phase 3 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Message Section | Message Section | Individual chat section | 3 | XS | Frontend | Responsive | Phase 3 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Message Section | Message Section | Individual chat settings | 3 | XS | Frontend | Responsive | Phase 3 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Community Section | Community section | KPIs, Leaders follow section | 3 | XS | Frontend | Responsive | Phase 3 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Influencer Feed | Influencer Feed | Thought Leadership Posts, Inspiring Videos, Case Studies, AMA Highlights | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Influencer Feed | Influencer Feed | Commenting, Liking, Sharing,Mute Topics,Follow / Unfollow Topics,Report Content | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Contribution | Contribution | Ask Questions, Share Case Studies, Run Polls, Publish Short Insights / Articles | 3 | XS | Frontend | Responsive | Phase 1 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
101 | Contribution | Contribution | Tag Peers, Topic-based Discussions, Anonymous Posting | 3 | XS | Frontend | Responsive | Phase 2 |  | 3.9 | 0 |  | 3.9 | [5 empty] | 0.78 | 6 | 14.58 |  |  | 15 |  | 15
| Resource Library | Resource Library | eBooks, Templates, Checklists | 3 | XS | Frontend | Responsive | Phase 2 |  | 6.9 | 0 |  | 6.9 | [5 empty] | 1.38 | 6 | 21.18 |  |  | 12 |  | 12
| Resource Library | Resource Library | Categorization by Topic/Role, Search & Filter Resources | 3 | XS | Frontend | Responsive | Phase 2 |  | 6.9 | 0 |  | 6.9 | [5 empty] | 1.38 | 6 | 21.18 |  |  | 12 |  | 12
| Resource Library | Resource Library | User Ratings & Reviews, Bookmark / Save for Later | 3 | XS | Frontend | Responsive | Phase 2 |  | 6.9 | 0 |  | 6.9 | [5 empty] | 1.38 | 6 | 21.18 |  |  | 12 |  | 12
| Events & AMAs | Events & AMAs | Upcoming Live Sessions, Recording Library, Topic Filters / Search | 3 | XS | Frontend | Responsive | Phase 2 |  | 18.9 | 0 |  | 18.9 | [5 empty] | 3.78 | 6 | 47.58
| Events & AMAs | Events & AMAs | Ask Questions Live, Chat with Attendees, RSVP / Calendar Integration | 3 | S | Frontend | Responsive | Phase 2 |  | 40.95 | 0 |  | 40.95 | [5 empty] | 8.19 | 12 | 102.09
| Buyer’s Guide / Sponsors | Buyer’s Guide / Sponsors | Contextual Sponsored Insights, Featured Recommendations | 3 | XS | Frontend | Responsive | Phase 2 |  | 18.9 | 0 |  | 18.9 | [5 empty] | 3.78 | 6 | 47.58
| Buyer’s Guide / Sponsors | Buyer’s Guide / Sponsors | User Ratings & Reviews, Lead Capture for Vendors | 3 | XS | Frontend | Responsive | Phase 1 |  | 18.9 | 0 |  | 18.9 | [5 empty] | 3.78 | 6 | 47.58
| Recognition & Reputation | Recognition & Reputation | Achievement Badges, Contribution Streaks | 3 | XS | Frontend | Responsive | Phase 2 |  | 18.9 | 0 |  | 18.9 | [5 empty] | 3.78 | 6 | 47.58
| Recognition & Reputation | Recognition & Reputation | Verified HR Credentials, Community Reputation Score | 3 | XS | Frontend | Responsive | Phase 2 |  | 18.9 | 0 |  | 18.9 | [5 empty] | 3.78 | 6 | 47.58
| Analytics | Analytics | Topic Trends, Engagement Stats | 3 | S | Frontend | Responsive | Phase 3 |  | 40.95 | 0 |  | 40.95 | [5 empty] | 8.19 | 12 | 102.09
| Analytics | Analytics | Anonymized Insights, Content Performance, Audience Segmentation | 3 | XS | Frontend | Responsive | Phase 3 |  | 18.9 | 0 |  | 18.9 | [5 empty] | 3.78 | 6 | 47.58
| Trust & Safety | Trust & Safety | Human + AI Moderation, Abuse / Spam Reporting | 3 | XS | Frontend | Responsive | Phase 2 |  | 18.9 | 0 | 40 | 18.9 | [5 empty] | 3.78 | 6 | 87.58
| Trust & Safety | Trust & Safety | Community Guidelines, Privacy Controls / Data Management | 3 | XS | Frontend | Responsive | Phase 2 |  | 18.9 | 0 |  | 18.9 | [5 empty] | 3.78 | 6 | 47.58
101 | Confessional Corner | Confessional Corner | Sensitive Topics Collaboration, Optional Expert Input, Thread Privacy Controls | 3 | XS | Frontend | Responsive | Phase 1 |  | 18.9 | 0 |  | 18.9 | [5 empty] | 3.78 | 6 | 47.58
| Settings | Settings | Connected Accounts | 3 | XS | Frontend | Responsive | Phase 2 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | Account Settings | Saved Posts, Archive Posts | 3 | XS | Frontend | Responsive | Phase 2 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | Billing/ for creators | Subscription Management | 3 | XS | Frontend | Responsive | Phase 3 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | Billing/ for creators | Creator tools, proffesional dashboard | 3 | XS | Frontend | Responsive | Phase 3 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | Settings | Topic Preferences | 3 | XS | Frontend | Responsive | Phase 2 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
101 | Settings | Settings | Feed Controls | 3 | XS | Frontend | Responsive | Phase 2 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | Settings | Anonymous Controls | 3 | XS | Frontend | Responsive | Phase 2 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | App Settings | General, theme settings | 1 | XS | Frontend | Responsive | Phase 2 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | App Settings | Notifications, language settings | 1 | XS | Frontend | Responsive | Phase 2 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | Settings | Block / Mute Users | 3 | XS | Frontend | Responsive | Phase 2 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | Privacy & Safety | Account Privacy | 3 | XS | Frontend | Responsive | Phase 1 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | Privacy & Safety | Private account / Account preferences | 3 | XS | Frontend | Responsive | Phase 1 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | About | Help Center | 3 | XS | Frontend | Responsive | Phase 1 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | About | Contact Support | 3 | XS | Frontend | Responsive | Phase 1 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | About | Deactivate Account | 3 | XS | Frontend | Responsive | Phase 1 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | About | Delete Account | 3 | XS | Frontend | Responsive | Phase 1 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Settings | Interactions | Messages, replies, tags, mentions, Comments, sharing | 3 | XS | Frontend | Responsive | Phase 2 |  | 2.9 | 0 |  | 2.9 | [5 empty] | 0.58 | 6 | 12.38 |  |  | 16 |  | 16
| Common Module | Admin Controls | Mgmt Screen for admin controls | 12 | S | Frontend | Responsive | Phase 3 |  | 40.95 | 0 |  | 40.95 | [5 empty] | 8.19 | 12 | 102.09
| Common Module | Admin Module | User Review and Act to delete or inactivate user User activity log Dashboard with emetrics on user patterns Resouce Mgmt Module | 12 | M | Frontend | Responsive | Phase 3 |  | 74.76 | 0 |  | 0 | [5 empty] | 14.952 | 20 | 109.712
| Bussiness Module | Profile Management |  | 0 | S | Backend | Responsive | Phase 1 |  | 0 | 46.74 |  | 0 | [5 empty] | 9.348 | 0 | 56.088 |  |  |  | 15
| Bussiness Module | Profile Management |  | 0 | S | Backend | Responsive | Phase 2 |  | 0 | 46.74 |  | 0 | [5 empty] | 9.348 | 0 | 56.088 |  |  |  | 15
| Bussiness Module | On-Boarding Process |  | 0 | XS | Backend | Responsive | Phase 1 |  | 0 | 25.115 |  | 0 | [5 empty] | 5.023 | 0 | 30.138 |  |  |  | -8
| Bussiness Module | On-Boarding Process |  | 0 | XS | Backend | Responsive | Phase 2 |  | 0 | 25.115 |  | 0 | [5 empty] | 5.023 | 0 | 30.138 |  |  |  | -8
| Bussiness Module | Feed and Post Management |  | 0 | S | Backend | Responsive | Phase 1 |  | 0 | 61.74 |  | 0 | [5 empty] | 12.348 | 0 | 74.088
| Bussiness Module | Feed and Post Management |  | 0 | XS | Backend | Responsive | Phase 2 |  | 0 | 33.115 |  | 0 | [5 empty] | 6.623 | 0 | 39.738 |  |  |  | -16
| Bussiness Module | Collaboration | Topic-based Discussions, Anonymous Posting , Anonymous Discussions | 0 | S | Backend | Responsive | Phase 1 |  | 0 | 61.74 |  | 0 | [5 empty] | 12.348 | 0 | 74.088
| Bussiness Module | Collaboration | Topic-based Discussions, Anonymous Posting , Anonymous Discussions | 0 | XS | Backend | Responsive | Phase 2 |  | 0 | 33.115 |  | 0 | [5 empty] | 6.623 | 0 | 39.738 |  |  |  | -16
| Bussiness Module | Event Management | Upcoming Live Sessions, Recording Library, Topic Filters / Search Ask Questions Live, Chat with Attendees, RSVP / Calendar Integration | 0 | M | Backend | Responsive | Phase 1 |  | 0 | 97.44 |  | 0 | [5 empty] | 19.488 | 0 | 116.928
| Bussiness Module | Event Management | Upcoming Live Sessions, Recording Library, Topic Filters / Search Ask Questions Live, Chat with Attendees, RSVP / Calendar Integration | 0 | S | Backend | Responsive | Phase 2 |  | 0 | 61.74 |  | 0 | [5 empty] | 12.348 | 0 | 74.088
| Bussiness Module | Filter and Searching | Unified Search Bar, Search Filters ,AI Semantic Search, Search Suggestions, Recent Searches | 0 | S | Backend | Responsive | Phase 3 |  | 0 | 61.74 | 40 | 0 | [5 empty] | 12.348 | 0 | 114.088
| Bussiness Module | Upload and Download management |  | 0 | S | Backend | Responsive | Phase 1 |  | 0 | 61.74 |  | 0 | [5 empty] | 12.348 | 0 | 74.088
| Bussiness Module | Help & Support |  | 0 | S | Backend | Responsive | Phase 2 |  | 0 | 61.74 |  | 0 | [5 empty] | 12.348 | 0 | 74.088
| Bussiness Module | Dashboard & Analytics |  | 0 | M | Backend | Responsive | Phase 3 |  | 0 | 97.44 |  | 0 | [5 empty] | 19.488 | 0 | 116.928
| Bussiness Module | Action Module | Chat, Comment, Like, Share, Rate and Review. This a independent module which can be attach to any module like feed, live-streaming, posts, Help & support | 0 | L | Backend | Responsive | Phase 2 |  | 0 | 159.6 |  | 0 | [5 empty] | 31.92 | 0 | 191.52
| Bussiness Module | Subscription Management |  | 0 | S | Backend | Responsive | Phase 1 |  | 0 | 61.74 |  | 0 | [5 empty] | 12.348 | 0 | 74.088
| Common Module | Streaming service | Real-Time Communication | 0 | M | Backend | Responsive | Phase 1 |  | 0 | 97.44 |  | 0 | [5 empty] | 19.488 | 0 | 116.928
| Common Module | Anonymous Control |  | 0 | M | Backend | Responsive | Phase 2 |  | 0 | 97.44 |  | 0 | [5 empty] | 19.488 | 0 | 116.928
| Common Module | Notification managment |  | 0 | S | Backend | Responsive | Phase 1 |  | 0 | 61.74 |  | 0 | [5 empty] | 12.348 | 0 | 74.088
| Common Module | Data Security and Data Privacy |  | 0 | M | Backend | Responsive | Phase 2 |  | 0 | 97.44 |  | 0 | [5 empty] | 19.488 | 0 | 116.928
| Common Module | Payment Gateway |  | 0 | S | Backend | Responsive | Phase 3 |  | 0 | 61.74 |  | 0 | [5 empty] | 12.348 | 0 | 74.088
| Common Module | CMS |  | 0 | S | Backend | Responsive | Phase 1 |  | 0 | 61.74 |  | 0 | [5 empty] | 12.348 | 0 | 74.088
| Common Module | Authentication |  | 0 | XS | Backend | Responsive | Phase 1 |  | 0 | 17.115 |  | 0 | [5 empty] | 3.423 | 0 | 20.538
| Common Module | RBAC |  | 0 | XS | Backend | Responsive | Phase 1 |  | 0 | 17.115 |  | 0 | [5 empty] | 3.423 | 0 | 20.538
| Common Module | Cache managment |  | 0 | XS | Backend | Responsive | Phase 1 |  | 0 | 17.115 |  | 0 | [5 empty] | 3.423 | 0 | 20.538
| Common Module | User managment |  | 0 | XS | Backend | Responsive | Phase 2 |  | 0 | 17.115 |  | 0 | [5 empty] | 3.423 | 0 | 20.538
| Common Module | Monitoring |  | 0 | M | Backend | Responsive | Phase 2 |  | 0 | 97.44 |  | 0 | [5 empty] | 19.488 | 0 | 116.928
| Common Module | Audit-history |  | 0 | XS | Backend | Responsive | Phase 2 |  | 0 | 17.115 |  | 0 | [5 empty] | 3.423 | 0 | 20.538
| Common Module | Archival |  | 0 | M | Backend | Responsive | Phase 3 |  | 0 | 97.44 |  | 0 | [5 empty] | 19.488 | 0 | 116.928
| Common Module | Orchestration Module |  | 0 | S | Backend | Responsive | Phase 1 |  | 0 | 61.74 | 80 | 0 | [5 empty] | 12.348 | 0 | 154.088
| Common Module | Admin Management | User Review and Act to delete or inactivate user User activity log Dashboard with emetrics on user patterns Resouce Mgmt Module | 0 | M | Backend | Responsive | Phase 3 |  | 0 | 97.44 |  | 0 | [5 empty] | 19.488 | 0 | 116.928
Common | Database | Database script management |  |  | XS | Backend | Responsive | Phase 1 |  | 0 | 40 |  | 0 | [5 empty] | 0 | 0 | 40
Common | DevOps | Infrastructure Setup Pipeline Setup |  |  | S | Backend | Responsive | Phase 1 |  | 0 |  |  | 0 | 64 |  |  |  |  | 0 | 0 | 64 |  |  |  | 4
Common | Feedback & Bug fixing |  |  |  | XS | Backend | Responsive | Phase 1 |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0
Common | Overheads (PM, PO, Arch) |  |  |  | XS | Backend | Responsive | Phase 1 |  | 0 |  |  | 0 |  | 40 | 40 |  | 32 | 0 | 0 | 112
Common | Database | Database script management |  |  | XS | Backend | Responsive | Phase 2 |  | 0 | 32 |  | 0 | [5 empty] | 0 | 0 | 32
Common | DevOps | Infrastructure Setup Pipeline Setup |  |  | S | Backend | Responsive | Phase 2 |  | 0 |  |  | 0 | 32 |  |  |  |  | 0 | 0 | 32 |  |  |  | 4
Common | Feedback & Bug fixing |  |  |  | XS | Backend | Responsive | Phase 2 |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0
Common | Overheads (PM, PO, Arch) |  |  |  | XS | Backend | Responsive | Phase 2 |  | 0 |  |  | 0 |  | 40 | 40 |  | 32 | 0 | 0 | 112
Common | Database | Database script management |  |  | XS | Backend | Responsive | Phase 3 |  | 0 | 24 |  | 0 | [5 empty] | 0 | 0 | 24
Common | DevOps | Infrastructure Setup Pipeline Setup |  |  | S | Backend | Responsive | Phase 3 |  | 0 |  |  | 0 | 32 |  |  |  |  | 0 | 0 | 32 |  |  |  | 4
Common | Feedback & Bug fixing |  |  |  | XS | Backend | Responsive | Phase 3 |  | 0 |  |  | 0 | [5 empty] | 0 | 0 | 0
Common | Overheads (PM, PO, Arch) |  |  |  | XS | Backend | Responsive | Phase 3 |  | 0 |  |  | 0 |  | 40 | 40 |  | 24 | 0 | 0 | 104
|  |  | Totals | 0 |  |  |  |  | 0 | 629.51 | 2009.775 | 224 | 554.75 | 128 | 120 | 120 | 0 | 88 | 508.657 | 482 | 4864.692 | 4864.692

## Efforts Summary
Total
|  |  |  | 0 |  | Function | Actuals | Ratio | Other Fucntions Split | Total | Approx | Rate
|  |  |  | 629.51 |  | Mobile Delivery | 554.75 | 16.23% | 234.7937 | 789.5437 | 20% | 36152
|  |  |  | 2009.775 |  | Web Delivery | 629.51 | 18.42% | 266.4353 | 895.9453 | 20% | 36152
|  |  |  | 224 |  | Backend Delivery | 2233.775 | 65.35% | 945.4281 | 3179.2031 | 60% | 108456
|  |  |  | 554.75 | [5 empty] | 4864.692 |  | 180760
508.657
482
|  |  |  | 128 |  | Other functions (QA+PO+PM+Architect) | 1446.657
120
120
0
88
| 1694.092 | 1934.988 | 1235.612 | 4864.692 |  | Home
Team Size (Not updated)
Design | 1 | 1 | 1
Development | 6.6 | 6.6 | 3.3
AI | 1 | 1 | 1
QA Manual | 2 | 2 | 1
QA Auto | 2 | 2 | 1
DevOps | 1 | 1 | 1
PO | 1 | 1 | 1
Scrum | 1 | 1 | 1
Design Strategist | 1 | 1 | 1
Tech Architect | 1 | 1 | 1
| 1.05 | 1.25 | 1.55 | <-- Calendar Months
Team | Phase 1 | Phase 2 | Phase 3 | Total Efforts | Seniority
Engg Lead | 1.05 | 1.25 | 1.55 | 3.85 | Tech Lead
Engg Developer | 1.05 | 1.25 | 1.55 | 3.85 | Developer - IC
Engg Developer | 1.05 | 1.25 | 1.55 | 3.85 | Jr. Developer - IC
Engg Developer | 1.05 | 1.25 | 1.55 | 3.85 | Developer - IC
Engg Lead | 1.05 | 1.25 | 1.55 | 3.85 | Tech Lead
Engg Developer | 1.05 | 1.25 | 1.55 | 3.85 | Developer - IC
Engg Developer | 1.05 | 1.25 | 1.55 | 3.85 | Jr. Developer - IC
Engg Developer | 1.05 | 1.25 | 1.55 | 3.85 | Developer - IC
AI Engineer | 0.75 | 0.4 | 0.25 | 1.4 | AI Engineer
Functional QA Engr | 0.6 | 0.65 | 0.8 | 2.05 | Functional QA - IC
Auto QA Engr | 0.5 | 0.7 | 0.8 | 2 | QA Engineer - IC
Functional QA Engr | 0.6 | 0.65 | 0.8 | 2.05 | Functional QA - IC
Auto QA Engr | 0.5 | 0.7 | 0.8 | 2 | QA Engineer - IC
QA Lead | 0.2 | 0.3 | 0.35 | 0.85 | QA Lead
Principal Tech Lead | 0.35 | 0.4 | 0.5 | 1.25 | Principal Tech Lead
DevOps Engr | 0.4 | 0.2 | 0.2 | 0.8 | Developer - IC
PO | 0.45 | 0.5 | 0.65 | 1.6 | Product Owner
PM | 0.35 | 0.4 | 0.5 | 1.25 | Project Manager
Delivery Manager | 0.7 | 0.85 | 1.05 | 2.6 | Delivery Manager
Total Efforts | 13.8 | 15.75 | 19.1 | 48.65
| 2208 | 2520 | 3056 | 7784
Backend: Java Spring (v5.3+), JDK 17, MySQL 8.4
Frontend: Angular / React (TBD)
CI/CD: Jenkins, jFrog, SonarQube
Authentication: OKTA SSO, OAuth 2.0, RBAC/ACL
Hosting & Infra: VM-based deployment with environment segregation
Testing: JUnit, Selenium, Postman (API automation)

## Scope Summary
Phase 1 |  |  | Phase 2 |  |  | Phase 3
Module | Feature | Sub Feature | Persona | Module | Feature | Persona | Module | Feature
Registration | Registration | Email Signup | Registration | Registration | Google Signup | Registration | Registration | Invite-Based Registration
Identification | Identification | Email Login | Registration | Registration | Linkedin Signup | Discovery | Discovery | Search Suggestions
First Time Experience | First Time Experience | Role & Profile Setup | Identification | Identification | Linkedin Login | Discovery | Global Search | People to follow
First Time Experience | First Time Experience | Topic Preferences | Identification | Identification | Google Login | Account Profile | User Profile | Proffesional experience section
Discovery | Discovery | Unified Search Bar | Identification | Identification | Session Management | Account Profile | User Profile | List of own posts
Discovery | Discovery | Search Filters | First Time Experience | First Time Experience | Welcome Flow | Notification Hub | Notification Hub | Push Notifications
Account Profile | Account Profile | Basic Profile, KPIs | First Time Experience | First Time Experience | First Action Nudges | Message Section | Message Section | List of People, search function
Account Profile | Account Profile | Privacy Controls | Discovery | Discovery | AI Semantic Search | Message Section | Message Section | Individual chat section
Notification Hub | Notification Hub | In-App Alerts | Discovery | Discovery | Recent Searches | Message Section | Message Section | Individual chat settings
Notification Hub | Notification Hub | Email Notifications | Account Profile | Account Profile | Activity Overview | Community Section | Community section | KPIs, Leaders follow section
Personalized Home Feed | Personalized Home Feed | Content Feed | Account Profile | Account Profile | Badges & Contributions | Analytics | Analytics | Topic Trends, Engagement Stats
Personalized Home Feed | Home Feed | Create new post | Notification Hub | Notification Hub | Notification Settings | Analytics | Analytics | Anonymized Insights, Content Performance, Audience Segmentation
Personalized Home Feed | Personalized Home Feed | Feed Personalization | Influencer Feed | Influencer Feed | Thought Leadership Posts, Inspiring Videos, Case Studies, AMA Highlights | Settings | Billing/ for creators | Subscription Management
Personalized Home Feed | Personalized Home Feed | Interaction | Influencer Feed | Influencer Feed | Commenting, Liking, Sharing,Mute Topics,Follow / Unfollow Topics,Report Content | Settings | Billing/ for creators | Creator tools, proffesional dashboard
Personalized Home Feed | Home Feed | Comments screen, interaction | Contribution | Contribution | Tag Peers, Topic-based Discussions, Anonymous Posting | Common Module | Admin Controls | Mgmt Screen for admin controls
Personalized Home Feed | Home Feed | Share post interaction | Resource Library | Resource Library | eBooks, Templates, Checklists | Common Module | Admin Module | User Review and Act to delete or inactivate user User activity log Dashboard with emetrics on user patterns Resouce Mgmt Module
Contribution | Contribution | Ask Questions, Share Case Studies, Run Polls, Publish Short Insights / Articles | Resource Library | Resource Library | Categorization by Topic/Role, Search & Filter Resources | Bussiness Module | Filter and Searching | Unified Search Bar, Search Filters ,AI Semantic Search, Search Suggestions, Recent Searches
Buyer’s Guide / Sponsors | Buyer’s Guide / Sponsors | User Ratings & Reviews, Lead Capture for Vendors | Resource Library | Resource Library | User Ratings & Reviews, Bookmark / Save for Later | Bussiness Module | Dashboard & Analytics
Confessional Corner | Confessional Corner | Sensitive Topics Collaboration, Optional Expert Input, Thread Privacy Controls | Events & AMAs | Events & AMAs | Upcoming Live Sessions, Recording Library, Topic Filters / Search | Common Module | Payment Gateway
Settings | Privacy & Safety | Account Privacy | Events & AMAs | Events & AMAs | Ask Questions Live, Chat with Attendees, RSVP / Calendar Integration | Common Module | Archival
Settings | Privacy & Safety | Private account / Account preferences | Buyer’s Guide / Sponsors | Buyer’s Guide / Sponsors | Contextual Sponsored Insights, Featured Recommendations | Common Module | Admin Management | User Review and Act to delete or inactivate user User activity log Dashboard with emetrics on user patterns Resouce Mgmt Module
Settings | About | Help Center | Recognition & Reputation | Recognition & Reputation | Achievement Badges, Contribution Streaks
Settings | About | Contact Support | Recognition & Reputation | Recognition & Reputation | Verified HR Credentials, Community Reputation Score
Settings | About | Deactivate Account | Trust & Safety | Trust & Safety | Human + AI Moderation, Abuse / Spam Reporting
Settings | About | Delete Account | Trust & Safety | Trust & Safety | Community Guidelines, Privacy Controls / Data Management
Bussiness Module | Profile Management |  | Settings | Settings | Connected Accounts
Bussiness Module | On-Boarding Process |  | Settings | Account Settings | Saved Posts, Archive Posts
Bussiness Module | Feed and Post Management |  | Settings | Settings | Topic Preferences
Bussiness Module | Collaboration | Topic-based Discussions, Anonymous Posting , Anonymous Discussions | Settings | Settings | Feed Controls
Bussiness Module | Event Management | Upcoming Live Sessions, Recording Library, Topic Filters / Search Ask Questions Live, Chat with Attendees, RSVP / Calendar Integration | Settings | Settings | Anonymous Controls
Bussiness Module | Upload and Download management |  | Settings | App Settings | General, theme settings
Bussiness Module | Subscription Management |  | Settings | App Settings | Notifications, language settings
Common Module | Streaming service | Real-Time Communication | Settings | Settings | Block / Mute Users
Common Module | Notification managment |  | Settings | Interactions | Messages, replies, tags, mentions, Comments, sharing
Common Module | CMS |  | Bussiness Module | Profile Management
Common Module | Authentication |  | Bussiness Module | On-Boarding Process
Common Module | RBAC |  | Bussiness Module | Feed and Post Management
Common Module | Cache managment |  | Bussiness Module | Collaboration | Topic-based Discussions, Anonymous Posting , Anonymous Discussions
Common Module | Orchestration Module |  | Bussiness Module | Event Management | Upcoming Live Sessions, Recording Library, Topic Filters / Search Ask Questions Live, Chat with Attendees, RSVP / Calendar Integration
|  |  | Bussiness Module | Help & Support
|  |  | Bussiness Module | Action Module | Chat, Comment, Like, Share, Rate and Review. This a independent module which can be attach to any module like feed, live-streaming, posts, Help & support
|  |  | Common Module | Anonymous Control
|  |  | Common Module | Data Security and Data Privacy
|  |  | Common Module | User managment
|  |  | Common Module | Monitoring
|  |  | Common Module | Audit-history

## Guidelines (hidden)
CONSOLIDATED EFFORTS SUMMARY | SERVICES | DESIGN (Responsive) | WEB UI (Responsive) | DESIGN (Web) | WEB UI (Web) | DESIGN (Mobile) | NATIVE (Mobile) | HYBRID (Mobile) | NATIVE (Responsive) | HYBRID (Responsive) | Auto QA UI | Auto QA Services
XL | 261.24 | 52.8 | 167.79 | 33 | 141.246 | 24.2 | 90.3 | 111.3 | 107.1 | 132.3 | 48 | 48
L | 159.6 | 26.4 | 115.71 | 22 | 91.224 | 16.5 | 54.6 | 71.4 | 71.4 | 88.2 | 32 | 40
M | 97.44 | 16.5 | 74.76 | 12.1 | 53.256 | 12.1 | 33.6 | 42 | 44.1 | 54.6 | 20 | 32
S | 61.74 | 8.8 | 40.95 | 4.4 | 30.324 | 4.4 | 18.9 | 23.1 | 25.2 | 29.4 | 12 | 24
S | 35.7 | 6.6 | 22.68 | 3.3 | 16.212 | 2.2 | 10.5 | 12.6 | 14.7 | 16.8 | 8 | 16
XS | 17.115 | 4.4 | 18.9 | 2.2 | 12.6 | 1.1 | 8.4 | 8.4 | 10.5 | 12.6 | 6 | 10
Form Factor Lookup | Design | UI | Automation UI | Automation Services
Responsive | 3 | 4 | 12 | 13
Web | 5 | 6 | 12 | 13
Mobile Native | 7 | 8 | 12 | 13
Mobile Hybrid | 7 | 9 | 12 | 13
DESIGN | Desktop + Mobile |  |  | Web Only |  |  | Mobile Responsive |  |  | Mobile App Only
| Design | IxD | UID | Design | IxD | UID | Design | IxD | UID | Design | IxD | UID
XL | 48 | 22 | 26 | 30 | 13 | 17 | 18 | 7 | 11 | 22 | 9 | 13
L | 24 | 11 | 13 | 20 | 9 | 11 | 11 | 4.5 | 6.5 | 15 | 6.5 | 8.5
M | 15 | 6.5 | 8.5 | 11 | 4.5 | 6.5 | 6 | 2 | 4 | 11 | 4.5 | 6.5
S | 8 | 2 | 6 | 4 | 1 | 3 | 3 | 1 | 2 | 4 | 2 | 2
WEB APP | Full Responsive | [5 empty] | Single Form Factor
| Web UI | UI Dev | Integration | Unit Testing | Dev Testing | Bug Fixing | Web UI | UI Dev | Integration | Unit Testing | Dev Testing | Bug Fixing
XL | 159.8 | 72 | 24 | 30 | 22 | 11.8 | 134.52 | 48 | 26 | 32 | 19.2 | 9.32
L | 110.2 | 48 | 16 | 20 | 18 | 8.2 | 86.88 | 32 | 16 | 20 | 12.8 | 6.08
M | 71.2 | 28 | 10 | 14 | 14 | 5.2 | 50.72 | 18 | 10 | 12 | 7.2 | 3.52
S | 39 | 18 | 4 | 6 | 8 | 3 | 28.88 | 12 | 4 | 6 | 4.8 | 2.08
S | 21.6 | 10 | 2 | 4 | 4 | 1.6 | 15.44 | 6 | 2 | 4 | 2.4 | 1.04
WEB SERVICES | [5 empty] | Website
| Development | Dev | Unit Test | Integration |  |  | HTML/CSS | CMS
XL | 68 | 40 | 20 | 8 |  | XL | 24 | 16
L | 40 | 22 | 12 | 6 |  | L | 16 | 12
M | 24 | 12 | 8 | 4 |  | M | 12 | 8
S | 16 | 8 | 6 | 2 |  | S | 8 | 4
S | 8 | 4 | 2 | 2 |  | S | 4 | 2
AUTOMATED QA | [5 empty] | PRODUCT OWNER
| Development | [5 empty] | % of Dev Time
XL | 32 |  |  |  |  | XL | 20%
L | 20 |  |  |  |  | L | 15%
M | 12 |  |  |  |  | M | 10%
S | 8 |  |  |  |  | S | 8%
S | 4 |  |  |  |  | S | 5%
NATIVE MOBILE | Mobile Only |  |  |  | Tablet + Mobile
| Development | UI Dev | Integration | Unit Testing | Development | UI Dev | Integration | Unit Testing
XL | 86 | 36 | 26 | 24 | 102 | 54 | 24 | 24
L | 52 | 20 | 16 | 16 | 68 | 36 | 16 | 16
M | 32 | 14 | 10 | 8 | 42 | 20 | 10 | 12
S | 18 | 10 | 4 | 4 | 24 | 16 | 4 | 4
S | 10 | 4 | 2 | 4 | 14 | 8 | 2 | 4
HYBRID MOBILE | Mobile Only |  |  |  | Tablet + Mobile
| Development | UI Dev | Integration | Unit Testing | Development | UI Dev | Integration | Unit Testing |  | 0
XL | 106 | 48 | 26 | 32 | 126 | 72 | 24 | 30
L | 68 | 32 | 16 | 20 | 84 | 48 | 16 | 20
M | 40 | 18 | 10 | 12 | 52 | 28 | 10 | 14
S | 22 | 12 | 4 | 6 | 28 | 18 | 4 | 6
S | 12 | 6 | 2 | 4 | 16 | 10 | 2 | 4
BACKEND SERVICES | Total | Dev | Unit Test | Integration | Dev Testing | Bug Fixing
XL | 90.4 | 40 | 20 | 8 | 16 | 6.4
L | 56 | 22 | 12 | 6 | 12 | 4
M | 34.4 | 12 | 8 | 4 | 8 | 2.4
S | 21.4 | 8 | 6 | 2 | 4 | 1.4
S | 13 | 4 | 2 | 2 | 4 | 1
XS | 6.5 | 2 | 1 | 1 | 2 | 0.5
BACKEND MODEL
| Total | Dev | Unit Test | Integration
XL | 68 | 40 | 20 | 8
L | 40 | 22 | 12 | 6
M | 24 | 12 | 8 | 4
S | 16 | 8 | 6 | 2
S | 8 | 4 | 2 | 2
XS | 4 | 2 | 1 | 1
BACKEND CONTROLLERS
| Total | Dev | Unit Test | Integration | Dev Testing | Bug Fixing
XL | 90.4 | 40 | 20 | 8 | 16 | 6.4
L | 56 | 22 | 12 | 6 | 12 | 4
M | 34.4 | 12 | 8 | 4 | 8 | 2.4
S | 21.4 | 8 | 6 | 2 | 4 | 1.4
S | 13 | 4 | 2 | 2 | 4 | 1
XS | 5.8 | 2 | 1 | 1 | 1 | 0.8
MANUAL QA
Basic (Primary one browser/OS testing for functionality) Testing Strategy Documentation Test Plan Documentation | 8%
Cross browser / Multi device / Multi OS / hardware specifications / multi network testing (No of permutations) | 4 | Depending on the scope, these combinations be figured out
Additional time added to Base QA time per permutation | 10% | Depending on the comlexity of the project this % could increase
Final % | 11.2%
ENGINEERING WORK
Engg deliverables (As part of source code) | 0.1 | Percentage | Repo maintanence: Github, bitbucket as per customer choice Source code linting : ESLint + TSLint (for typescript) Code profiling: SonarQube (All high and critical issues are eliminated before every Sprint release. Minute warnings are addressed on a case to case basis only if there is good ROI) Unit test coverage:. Runs every build and published during every sprint release Logging: Configurable logging onto Console, File System. CloudWatch connected (log monitoring open source software). Divami logging and log monitoring default settings: <LINK TO BE ADDED> Front end criticals: obfuscation, minification, compression, images handling/caching. / storage scoping. memory footprint, host utilisation Back end criticals: auth handling. token mgmt best practises, memory footprint mgmt., server (host) utilisation Basic encryption. organic concurrency handling, senstive data hashing (basic).
Tech Documentation & Reporting | 0.1 | Percentage | Inline documentation: <Divami specific tool used to expose this to readers will be mentioned here> SonarQube run report published during every sprint release Unit test coverage report published during every sprint release Functional flows, Solution architecture and Application architecture are produced and maintained during implementation - For the critical flows only. These are later added into the product spec Specific documentation for any 3rd Party Integrations. How we performed the specific integration. Any wrappers/enhancements etc. Key/Creds storage details and rotation policy (if applicable) API Documentation: Swagger Database Schema: ER diagrams Any additional flow charts for data movement, end of day processing, constant grow data maintanence, are documented Divami Operation Security Practises: <Document Link>
Dev Ops & CI/CD Artifacts | #REF! | Hours | Pipeline script&Docker script Certificate and protocols usage records: Details of location. Configurations chosen. E.g. SSL. DNS etc. Deployment model documentation Infra Bill of Materials Infra as code
Engineering Overall Buffer | 0
Desing Overall Buffer | 0
ADDITIONALS
Security Scanning (Code & APIs)
Performance Testing
Load Testing
DB Tuning (Advanced) (Additional)
Maintanenence work (post release)
Infra Security / Environment security
High availability and uptime plan + DR
Application level monitoring framework on top of logs
API based functional testing
|  |  |  | Weeks | PoC
|  |  | PO | 4 | 100%
|  |  | Designer | 2 | 100%
|  |  | TL | 2 | 60%
|  |  | Engg | 6 | 60%

## Architecture - Techstack
Tech Stack
Frontend | React, ReactNative
Backend | NestJS
Database | Postgres, Neptune, DynamoDB, Redshit
Cloud | AWS

## Effort Table- Delete Later
India | High |  |  |  | Column #:
GenHRX | Role | Phase 1 | Phase 2 | Phase 3 | Total Efforts
Tech Lead | Engg Lead | 1.95 | 2.5 | 1.25 | 5.7
Engineer | Engg Developer | 1.95 | 2.5 | 1.25 | 5.7
Jr. Engineer | Engg Developer | 1.95 | 2.5 | 1.25 | 5.7
Jr. Engineer | Engg Developer | 1.95 | 2.5 | 1.25 | 5.7
AI Engineer | AI Engineer | 0.25 | 0.4 | 0.25 | 0.9
Functional QA | Functional QA Engr | 1.05 | 1.3 | 0.6 | 2.95
QA Engineer | Auto QA Engr | 0.95 | 1.35 | 0.65 | 2.95
Sr. QA Engineer | QA Lead | 0.25 | 0.35 | 0.2 | 0.8
Principal Tech Lead | Principal Tech Lead | 0.4 | 0.5 | 0.25 | 1.15
Engineer | DevOps Engr | 0.4 | 0.2 | 0.2 | 0.8
Product Owner | PO | 0.5 | 0.65 | 0.35 | 1.5
Jr. Project Manager | PM | 0.4 | 0.5 | 0.25 | 1.15
Delivery Manager | Delivery Manager | 0.65 | 0.85 | 0.45 | 1.95
|  | 12.65 | 16.1 | 8.2 | 36.95

## Questions
Naveen
Presenation like what we did for MPI
Fill all the tech needs just like MPI
Saikamal
Project Plan with Road Map
Customer has some technical questions, which we do not knwo at this point of time
Customer asking if Naveen can attend the call
Gopal
Solution Architecture
Infra Architecture
Costing of Infra
| Storage engine details | What we choose and how do we manager Content coming from User (Posts, Chats, Resources) - Storage as such and Search Index - Here we need to make a call on how do we seperate and manage or we keep all at once (Elastic Search doubles up as storage as well as index for Unstructured content) - Issue is linking between users and their respective content pointers (this piece could be managed separately?)
Performance in Search and Listing
Harsha
We need to provide the direction to the implementation
Define MVP in design
Connect it with Engineering plan
Rakesh | 1. Tech stack
2. Managing the storage (Resoruces and Library Module)
3. Uploading files (Question around storage size)
4. Newsfeed (Contnet feed management)
What are we building in the MVP and why? -Was asking for end-to-end platform - Milestone wise differentation
Key Modules | -Onbaording
-Feed discovery and creating content
-Discussion rooms ( this will lead to summary)
-Marketplace(Intent based discovery or search based)
- Resoruces and Library
-Profile and settings
Why CLPG | High level vision for the MVP ( Community led product growth) | Start small and grow
- Expression of thought and enagement (Reword this something around engagement realted to building online communities)
| - Access to thought leadership contnet | Infleuncers can bring more HR folks onto the paltform
| - Trusted and proven resources (Libraray) | Lived examples of HR that can be used by the community (Example of bringing therapy dog)
Features under these three pillars
Engineering | AI search
| Storage ¦ There is also personal storage aspect to it | Performance is always critical
| Understadnign the coomunity | Community to the content | Search on top of it
| Purpose | Contents
Slide-1
Slide-2 | Contents | Table of contents
Slide-3 | Executive Summary
Slide-4 | The vision
Slide-5 | Focus areas features
Slide-6 | Solution archtiecure
Slide-7 | Runtime
Slide-8 | Question and answers
Slide-9 | Security,storage, media, search, AI, performance and scalability, Comliance (GDPR, PII, DPDP) How do we monitor the content Human assitance and AI should be answered in security)
Slide-10
Slide-11
Slide-12
Slide-13
Slide-14
Slide-15
Slide-16
Slide-17
Slide-18
Slide-19
Slide-20
Slide-21
Slide-22
Slide-23
Slide-24
Slide-25
Slide-26
Slide-27
Slide-28

## Features under the three Pillar
Engagement | Thought leadership content | Resoruces Library
Community & Collaboration | Insights & Thought Leadership | Resources & Knowledge